## Sheet1
Project Ground Zero: Code Challenge 1

TEAM CONTACT INFO
Member	Phone	email			Actual Time	Time Estimate	Member	Completed	Task
Grant	503-758-9036	grant@superiorperformer.com			3	1	Seth	x	two team journal entries: one for each week of the class so far. Write a couple short paragraphs.
Richard	503-747-8897	berchapman@gmail.com			0.5	0.5	Seth	x	Client Estimate email
Seth	857-212-6797	sleamer@hotmail.com			1	1	Seth	x	In each week's journal entry, list the team's top five concepts for the week.
					1	Grant		choose some picture from the web
					1	Grant		Float the week's picture left in the first week's article and right in the second week's article.
SCHEDULE					0.5	Grant		Make sure the week's article text flows around the picture.
Day	Grant	Richard	Seth		1	1	Seth		Choose two color palettes,
Friday	All day	All day	12pm-12am			0.5	Seth			site when it is in full width
Saturday	7pm -12am	All day	All day				Seth			one when it is in narrow width.
Sunday	7pm -12am	All day	8am-12pm			1	Richard		Run your code through the Unicorn validator,
Monday	All day	All day	None			1	Richard		Remove any unused journal entries or code left over from the previous file
Tuesday	7pm -12am	All day	None			1	Richard		File management in Git
Wednesday	All day	All day	None			0.5	Richard		Delivery of site and email notification
Thursday	7pm -12am	All day	8am-12pm			0.5	All		Code Challenge
Friday	All day	All day	None		1	0.5	Seth		The team includes a final tally of their hours and a comparison to their estimate in their spreadsheet
					1	0	Seth		Git set up, and file structures for the web page/images/scripts/styles

					7.5	11

					Task order
TOTAL TIME ESTIMATE					x	Seth Sends Client Time Estimate: Say Friday 9am
					x	Richard Sets up repo for Git
Estimated Time to completion:		11	Hours		x	Seth Creates Content
					Grant gits image and imports content to Page
GIT HUB LINK					Seth Styles page
https://github.com/berchapman/groundzero.git					Richard validates and sends to repo
					Richard delivers site with all specifications
					The team includes a final tally of their hours and a comparison to their estimate in their spreadsheet
					Code Challenge

Project Issues
1. Setting up Git repository: Don't quite trust it, took longer than expected to get ducks in a row.
2. File naming conventions, Capitals, Underscores or dashes – need to have a standards sheet.
3. How to handle the repository, who holds the logistics of the files (ie reverting them if a mistake?)
4. QA: who tests the final product? Do we pass it to each other or an outside group?
5. Content takes longer than you think. Editing and formatting correctly.
6. do NOT look at open for files in the GitHub. Not updated correctly.